## Planned activities
N.O. | Activity | Subactivity | Status | Comments
1 | Goal document |  | Completed | Updated 16/11/2022
2 | Kick-off meeting |  | Not started | 2023-01-30
3 | Setting up Github with all files |  | Waiting for comments not sent | GitHub
4 | Literature review |  | On going
5 | Model development |  | On going
5.1 |  | Familarization with software | On going
5.2 |  | Model development | Not started
6 | Simulation study |  | Not started
6.1 |  | Economic control strategy | Not started
6.2 |  | Safety of supply temperature with varying weather conditions | Not started
6.3 |  | Live-coupling of the cloud-based system model with online available weather data and electrical grid frequency | Not started
6.4 |  | Optimization of the developed model | Not started
7 | Writing report |  | On going
7.1 | Introduction |  | Waiting for comments not sent
7.1.1 |  | Purpose and scope of the project | Waiting for comments not sent
7.1.2 |  | Research questions | Waiting for comments not sent
7.2 | Literature review |  | On going
7.3 | Background of the topic |  | Not started
7.3.1 |  | District heating systems | Not started
7.3.2 |  | Industrial heat pumps | Not started
7.3.3 |  | Thermal energy storage | Not started
7.3.4 |  | Other relevent topics | Not started
7.3.5 |  | Energy systems modelling | Not started
7.4 | Model development |  | Not started
7.4.1 |  | District heating network model | Not started
7.4.2 |  | Industrial heat pump model | Not started
7.4.3 |  | Thermal energy storage model | Not started
7.4.4 |  | Other equipment models | Not started
7.4.5 |  | Complete model | Not started
7.5 | Simulation study |  | Not started
7.5.1 |  | Economic control strategy | Not started
7.5.2 |  | Safety of supply temperature with varying weather conditions | Not started
7.5.3 |  | Live-coupling of the cloud-based system model with online available weather data and electrical grid frequency | Not started
7.5.4 |  | Optimization of the developed model | Not started
7.5.5 |  | Creating a web-application to demo the model | Not started
7.6 | Results and discussion |  | Not started
7.6.1 |  | Results | Not started
7.6.2 |  | Discussion | Not started
7.6.3 |  | Future work | Not started
7.7 | References |  | Not started
8 | Presentation |  | Not started
Completed
On going
Waiting for comments sent
Waiting for comments not sent
Not started